## Slide 1: MVY Part 150 Update
Martha’s Vineyard Airport (MVY)
Project Kickoff Meeting
October 19, 2022

## Slide 2: Agenda
Introductions
Scope of Work
  Project Schedule/Milestones
  Project Administration
FAA Coordination
Forecast and Noise Analysis

## Slide 3: Scope of Work
Five Major Elements to the Study
  ELEMENT 1. Project Management and Coordination
  ELEMENT 2. Design and Conduct a Public Consultation Program
  ELEMENT 3. Inventory
  ELEMENT 4. Aircraft Noise and Land Use Analysis
  ELEMENT 5. Prepare and Present Noise Exposure Map

## Slide 4: Project Schedule
Meeting / Activity | Anticipated Purpose | Anticipated Time Frame
Project Kick-Off Meeting | Define organizational and procedural matters and public outreach, review and refine scope and schedule details. | 4th Quarter 2022
TAC Meeting 1 and Public Meeting | Introduction to Part 150, discuss TAC member roles, identify issues of concern, discuss potential areas for noise monitoring, inform the public and take public comment | 1st Quarter 2023
TAC Meeting 2 | Presentation of noise modeling inputs; review forecast, review existing noise measures and upcoming noise measurement program | 2nd Quarter 2023
Noise Measurement Program | Obtain noise levels of individual aircraft overflights, significant non-aircraft noise sources, and background noise levels; measure sample DNL during peak activity season (summer) | 3rd Quarter 2023
TAC Meeting 3 | Presentation of noise monitoring data and the draft NEM document; | 3rd Quarter 2023
Public Comment Period and Public Meeting | Present the draft NEM and solicit public comments | 3rd Quarter 2023
Submission to FAA | MVY submits the Final NEM document to FAA for acceptance. | 4th Quarter 2023

## Slide 5: Administrative
Internal HMMH/MJ project team calls
  Discuss schedule, data needs, analysis and results
Monthly project meetings with MVY and MJ
  Identify preferred day and time
Coordination meetings with FAA and MADOT as needed

## Slide 6: FAA Coordination
Identify FAA representatives
  Who will be main POC for FAA on project (MVY and/or HMMH?)
  Desired frequency of communication
Determine with FAA their expected document / product review
  NEM Forecast
  Advisory committee members and/or presentations
  AEDT input review (if needed)
  NEM document review process
  Workshop presentations
Notes: Document / Product Not Needing Review
  Advisory committee presentations
  NEM Document review process
    Final Draft NEM (before public comment period)
    Final NEM (before submission to FAA)
  NCP Document review process
    Final Draft NCP (before public comment period)
    Final NCP (before submission to FAA)

## Slide 7: Advisory Committees
Advisory committees
  Technical Advisory Committee – TAC
Meeting schedule
  Three meetings over course of study
  Afternoon TAC meetings
Committee members
  Develop list of members for each committee
Meeting location

## Slide 8: Technical Advisory Committee
Representatives from:
Tenants
MVY
FAA –Tower
NBAA
AOPA
State / local agencies with land-use jurisdiction within the DNL 60 dB
  Dukes County
  MVC

## Slide 9: Forecast and Noise Analysis
Forecast
  Updated for year of submittal and five-year forecast
  2023/2028
Noise model version: AEDT 3e
Radar data
Noise monitoring and possible locations

## Slide 10: Discussion / Questions